## Cover
SHEET TAB LINKS
Gantt Chart
Gantt with Critical Path
Sprint Timeline
Cost
Actual work hours

## Critical Path
[6 empty] | 2020-08-11 | 2020-08-12 | 2020-08-13 | 2020-08-14 | 2020-08-15 | 2020-08-16 | 2020-08-17 | 2020-08-18 | 2020-08-19 | 2020-08-20 | 2020-08-21 | 2020-08-22 | 2020-08-23 | 2020-08-24
| Tasks | Path | Sprint | Hours |  | 2020-08-11: Date
|  |  |  | Projected | Critical | 08-11 | 08-12 | 08-13 | 08-14 | 08-15 | 08-16 | 08-17 | 08-18 | 08-19 | 08-20 | 08-21 | 08-22 | 08-23 | 08-24 | 30 hours per sprint
Design Implementation | [19 empty] | 10 hours per day | bar: 2020-08-11 to 2020-08-21; 2020-08-24
1 | Design Database | normal | 1 | 2 | 2 | bar: 2020-08-11
critical | bar: 2020-08-11
2 | Design Mobile Application | normal | 1 | 2 | 2 | bar: 2020-08-11
|  | critical | [17 empty] | LEGEND | bar: 2020-08-11
| Mobile Application Development | [18 empty] | Projected | bar: 2020-08-11 to 2020-08-14; 2020-08-17 to 2020-08-21; 2020-08-24
1 | Create IOS Development Environment | normal | 1 | 0.5 | 0.5 | [14 empty] | Critical | bar: 2020-08-11
|  | critical | 1 | bar: 2020-08-11
2 | Create Revision Repository Environement | normal | 1 | 0.5 | 0.5 | bar: 2020-08-11
|  | critical | 1 | bar: 2020-08-11
3 | Log In Page Controller | normal | 1 | 4 | 6 | bar: 2020-08-12
critical | bar: 2020-08-12 to 2020-08-13
4 | Registration Page Controller | normal | 1 | 4 | 6 | bar: 2020-08-12
critical | bar: 2020-08-12 to 2020-08-13
5 | Process Registration [Firebase] | normal | 1 | 3 | 5 | bar: 2020-08-12
critical | bar: 2020-08-12 to 2020-08-13
6 | Process Authentication[Firebase] | normal | 1 | 3 | 6 | bar: 2020-08-13
critical | bar: 2020-08-13 to 2020-08-14; 2020-08-17
7 | Home Page Controller | normal | 2 | 3 | 6 | bar: 2020-08-14
critical | bar: 2020-08-14; 2020-08-17 to 2020-08-18
8 | Realtime online users list [Firebase] | normal | 2 | 3 | 6 | bar: 2020-08-14
critical | bar: 2020-08-14; 2020-08-17 to 2020-08-18
9 | Create Board Controller | normal | 2 | 6 | 8 | bar: 2020-08-14
critical | bar: 2020-08-14; 2020-08-17 to 2020-08-18
10 | Handle Online Multiplayer Mode | normal | 2 | 12 | 14 | bar: 2020-08-14; 2020-08-17 to 2020-08-18
critical | bar: 2020-08-17 to 2020-08-20
11 | Transmit/Receive Player Moves [Firebase] | normal | 2 | 6 | 8 | bar: 2020-08-14; 2020-08-17 to 2020-08-18
critical | bar: 2020-08-17 to 2020-08-20
12 | Push Notifications | normal | 2 | 4 | 8 | bar: 2020-08-18
critical | bar: 2020-08-18 to 2020-08-19
13 | User Profile Controller | normal | 3 | 4 | 6 | bar: 2020-08-19 to 2020-08-21
critical | bar: 2020-08-21 to 2020-08-22
14 | Update User Profile | normal | 3 | 4 | 6 | bar: 2020-08-19 to 2020-08-21
critical | bar: 2020-08-21 to 2020-08-22
15 | Update User Profile in Firebase | normal | 3 | 4 | 6 | bar: 2020-08-20 to 2020-08-21
critical
16 | Handle Offline Mode | normal | 3 | 5 | 6 | bar: 2020-08-20 to 2020-08-21
critical | bar: 2020-08-20 to 2020-08-23
Database | bar: 2020-08-11 to 2020-08-14; 2020-08-17 to 2020-08-21; 2020-08-24
1 | Create Firebase Project | normal | 1 | 2 | 4 | bar: 2020-08-11
|  | critical | 2 | bar: 2020-08-17 to 2020-08-18
2 | Create Tables | normal | 1 | 3 | 6 | bar: 2020-08-11
|  | critical | 2 | bar: 2020-08-17 to 2020-08-18
Sprint Testing | bar: 2020-08-11 to 2020-08-14; 2020-08-17 to 2020-08-21; 2020-08-24
1 | Sprint #1 Test & Debugging | normal | 1 | 1 | 2 | bar: 2020-08-13
|  | critical | 1 | bar: 2020-08-13
2 | Sprint #2 Test & Debugging | normal | 2 | 2 | 6 | bar: 2020-08-18
|  | critical | 2 | bar: 2020-08-18 to 2020-08-19
3 | Sprint #3 Test & Debugging | normal | 3 | 4 | 8 | bar: 2020-08-21
|  | critical | 3
Documentation | bar: 2020-08-11 to 2020-08-14; 2020-08-17 to 2020-08-21; 2020-08-24
| Capstone II Document | normal | 3 | 8 | 10 | bar: 2020-08-20 to 2020-08-21
|  | critical | 3 | bar: 2020-08-21 to 2020-08-23
TOTAL HOURS: |  |  |  | 90 | 138

## Actual
[6 empty] | 2020-08-11 | 2020-08-12 | 2020-08-13 | 2020-08-14 | 2020-08-15 | 2020-08-16 | 2020-08-17 | 2020-08-18 | 2020-08-19 | 2020-08-20 | 2020-08-21 | 2020-08-22 | 2020-08-23 | 2020-08-24
| Tasks | Path | Sprint | Hours |  | 2020-08-11: Date
|  |  |  | Projected | Actual | 08-11 | 08-12 | 08-13 | 08-14 | 08-15 | 08-16 | 08-17 | 08-18 | 08-19 | 08-20 | 08-21 | 08-22 | 08-23 | 08-24 | 30 hours per sprint
Design Implementation | [19 empty] | 10 hours per day | bar: 2020-08-11 to 2020-08-21; 2020-08-24
1 | Design Database | normal | 1 | 2 | 2 | bar: 2020-08-11
actual | bar: 2020-08-11
2 | Design Mobile Application | normal | 1 | 2 | 2 | bar: 2020-08-11
|  | actual | [17 empty] | LEGEND | bar: 2020-08-11
| Mobile Application Development | [18 empty] | Projected | bar: 2020-08-11 to 2020-08-14; 2020-08-17 to 2020-08-21; 2020-08-24
1 | Create IOS Development Environment |  | 1 | 0.5 | 0.5 | [14 empty] | Critical | bar: 2020-08-11
2 | Create Revision Repository Environement |  | 1 | 0.5 | 0.5 | bar: 2020-08-11
3 | Log In Page Controller |  | 1 | 4 | 6 | bar: 2020-08-12
4 | Registration Page Controller |  | 1 | 4 | 6 | bar: 2020-08-12
5 | Process Registration [Firebase] |  | 1 | 3 | bar: 2020-08-12
6 | Process Authentication[Firebase] |  | 1 | 3 | bar: 2020-08-13
7 | Home Page Controller |  | 2 | 3 | bar: 2020-08-14
8 | Realtime online users list [Firebase] |  | 2 | 3 | bar: 2020-08-14
9 | Create Board Controller |  | 2 | 6 | bar: 2020-08-14
10 | Handle Online Multiplayer Mode |  | 2 | 12 | bar: 2020-08-14; 2020-08-17 to 2020-08-18
11 | Transmit/Receive Player Moves [Firebase] |  | 2 | 6 | bar: 2020-08-14; 2020-08-17 to 2020-08-18
12 | Push Notifications |  | 2 | 4 | bar: 2020-08-18
13 | User Profile Controller |  | 3 | 4 | bar: 2020-08-19 to 2020-08-21
14 | Update User Profile |  | 3 | 4 | bar: 2020-08-19 to 2020-08-21
15 | Update User Profile in Firebase |  | 3 | 4 | bar: 2020-08-20 to 2020-08-21
16 | Handle Offline Mode |  | 3 | 5 | bar: 2020-08-20 to 2020-08-21
1,3 | bar: 2020-08-12
Database | bar: 2020-08-11 to 2020-08-14; 2020-08-17 to 2020-08-21; 2020-08-24
1 | Create Firebase Project | normal | 1 | 2 | bar: 2020-08-11
|  | critical | 2
2 | Create Tables | normal | 1 | 3 | bar: 2020-08-11
|  | critical | 2
Sprint Testing | bar: 2020-08-11 to 2020-08-14; 2020-08-17 to 2020-08-21; 2020-08-24
1 | Sprint #1 Test & Debugging | normal | 1 | 1 | bar: 2020-08-13
|  | critical | 1 | bar: 2020-08-13
2 | Sprint #2 Test & Debugging | normal | 2 | 2 | bar: 2020-08-18
|  | critical | 2
3 | Sprint #3 Test & Debugging | normal | 3 | 4 | bar: 2020-08-21
|  | critical | 3
Documentation | bar: 2020-08-11 to 2020-08-14; 2020-08-17 to 2020-08-21; 2020-08-24
| Capstone II Document | normal | 3 | 8 | bar: 2020-08-20 to 2020-08-21
|  | critical | 3
TOTAL HOURS: |  |  |  | 90 | 17

## Cost
Resources | Quantity | Est Cost
Machines & Computers | 2 | $2399 est Macbook Pro tax excluded
Apple Developer Subscription | 1 | $299 USD tax excluded
Developers & Testers | 2 | $45/hr average mid level developers
Testing Devices(Iphones) | 2 | $1379 est price tax excluded
Internet Connection | 2 | $30 est on fibre connection tax excluded

## Gantt
[5 empty] | 2020-08-11 | 2020-08-12 | 2020-08-13 | 2020-08-14 | 2020-08-15 | 2020-08-16 | 2020-08-17 | 2020-08-18 | 2020-08-19 | 2020-08-20 | 2020-08-21
| Tasks |  | Sprint | Hours | 2020-08-11: Date
[5 empty] | 08-11 | 08-12 | 08-13 | 08-14 | 08-15 | 08-16 | 08-17 | 08-18 | 08-19 | 08-20 | 08-21 | 30 hours per sprint
Design Implementation | [15 empty] | 10 hours per day
1 | Design Database | normal | 1 | 2 | bar: Date 08-11
critical | bar: Date 08-11
2 | Design Mobile Application |  | 1 | 2 | bar: Date 08-11
Mobile Application Development | bar: Date 08-11 to Date 08-14; Date 08-17 to Date 08-21
1 | Create IOS Development Environment |  | 1 | 0.5 | bar: Date 08-11
2 | Create Revision Repository Environement |  | 1 | 0.5 | bar: Date 08-11
3 | Log In Page Controller |  | 1 | 4 | bar: Date 08-12
4 | Registration Page Controller |  | 1 | 4 | bar: Date 08-12
5 | Process Registration [Firebase] |  | 1 | 3 | bar: Date 08-12
6 | Process Authentication[Firebase] |  | 1 | 3 | bar: Date 08-13
7 | Home Page Controller |  | 2 | 3 | bar: Date 08-14
8 | Realtime online users list [Firebase] |  | 2 | 3 | bar: Date 08-14
9 | Create Board Controller |  | 2 | 6 | bar: Date 08-14
10 | Handle Online Multiplayer Mode |  | 2 | 12 | bar: Date 08-14; Date 08-17 to Date 08-18
11 | Transmit/Receive Player Moves [Firebase] |  | 2 | 6 | bar: Date 08-14; Date 08-17 to Date 08-18
12 | Push Notifications |  | 2 | 4 | bar: Date 08-18
13 | User Profile Controller |  | 3 | 4 | bar: Date 08-19 to Date 08-20
14 | Update User Profile |  | 3 | 4 | bar: Date 08-19 to Date 08-20
15 | Update User Profile in Firebase |  | 3 | 4 | bar: Date 08-20
16 | Handle Offline Mode |  | 3 | 5 | bar: Date 08-20 to Date 08-21
Database | bar: Date 08-11 to Date 08-14; Date 08-17 to Date 08-21
1 | Create Firebase Project |  | 1 | 2 | bar: Date 08-11
2 | Create Tables |  | 1 | 3 | bar: Date 08-11
Sprint Testing | bar: Date 08-11 to Date 08-14; Date 08-17 to Date 08-21
1 | Sprint #1 Test & Debugging |  | 1 | 1 | bar: Date 08-13
2 | Sprint #2 Test & Debugging |  | 2 | 2 | bar: Date 08-18
3 | Sprint #3 Test & Debugging |  | 3 | 4 | bar: Date 08-21
Documentation | bar: Date 08-11 to Date 08-14; Date 08-17 to Date 08-21
| Capstone II Document |  | 3 | 8 | bar: Date 08-21
TOTAL HOURS: |  |  |  | 90

## Sprints
DATE | SPRINT
| 1 | 2 | 3
2020-08-11
2020-08-12
2020-08-13
2020-08-14
2020-08-15 | FAMILY TIME. WEEKEND.
2020-08-16
2020-08-17
2020-08-18
2020-08-19
2020-08-20
2020-08-21
2020-08-22 | FAMILY TIME. WEEKEND.
2020-08-23
2020-08-24